## Graphics
100% |  | 86.05%
Last Update on the 23-02-2024 Online version is accessible here
a
89.47%
Half-days
Half-days
Usage of the scheduled project times until the product deadline
Days
Days
Usage of the days of the period from the first to the last project time

## Data
PS : "Excepted" and "Actual" percentages are the ones of |  | Week 1 |  | Week 2 |  | Week 3 |  | Week 4 |  | Week 5 |  | Week 6 |  | Week 7 |  | Week 8 |  | TOTALS |  |  |  | Data For Charts
THE END OF A WEEK |  | 8th Jan. - 12th Jan. |  | 15th Jan. - 19th Jan. |  | 22nd Jan. - 26th Jan. |  | 29th Jan. - 2nd Feb. |  | 5th Feb. - 9th Feb. |  | 12th Feb. - 16th Feb. |  | 19th Feb. - 23rd Feb. |  | 26th Feb. - 29th Feb. | [5 empty] | Date of today | 2024-02-23
Category | Name | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual | Expected | Actual |  |  |  |  | passed scheduled project times | 25 | half days | ( last half day : 23/02 afternoon )
Documents | Functional specifications |  |  | 0% | 2% | 90% | 40% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  |  | passed days from the first project time | 37 | days
Documents | Technical specifications |  |  | 0% | 0% | 70% | 25% | 90% | 80% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 1% |  |  |  |  | Remaining scheduled project times | 0
Documents | Management (Tasks, KPIs, Risks) |  |  | 0% | 5% | 80% | 70% | 100% | 90% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  |  | Remaining days from the first project time | 6
Documents | QA (test plan, test cases, documentation template) |  |  | 0% | 0% | 70% | 10% | 90% | 80% | 90% | 90% | 100% | 100% | 100% | 100% | 100% | 100% |  |  |  |  | product dead line | 2024-02-23
Code | Read an ASM file to build machine code |  |  | 0% | 0% | 90% | 60% | 100% | 85% | 100% | 98% | 100% | 95% | 100% | 100% | 100% | 100% |  |  |  |  | oral date | 2024-02-29
Code | read machine code to decode the instructions |  |  | 0% | 0% | 50% | 0% | 80% | 0% | 90% | 0% | 100% | 30% | 100% | 100% | 100% | 100% |  |  |  |  | total scheduled project days until final product | 29 | half days
Code | Execute each opcode trough the v-processor architecture |  |  | 0% | 0% | 70% | 30% | 90% | 30% | 100% | 30% | 100% | 80% | 100% | 100% | 100% | 100% |  |  |  |  | total scheduled time before oral presentation | 25 | half days
Code | Have a virtual terminal and a debugger |  |  | 0% | 0% | 10% | 10% | 40% | 10% | 50% | 10% | 70% | 10% | 100% | 60% | 100% | 60% |  |  |  |  | total days from the first to the last project time | 43 | days
Customer | User satisfaction |  |  | 0% | 0% | 50% | 60% | 60% | 60% | 70% | 40% | 80% | 40% | 100% | 40% | 100% | [5 empty] | total days from the first project time to the final product | 37 | days
Tasks progression | Tasks done/ready for review |  |  | 0 | 0 | 19 | 13 | 33 | 25 | 35 | 29 | 44 | 36 | 57 | 51 | 57 | 51 |  |  |  |  | day of the first project time | 2024-01-17
Human Ressources | Employee satisfaction |  |  | 90% | 64% | 90% | 64.17% | 90% | 71.67% | 90% | 71.67% | 90% | 78.33% | 90% | 80% | 90% | [7 empty] | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8
Human Ressources | Abscence time | 0h |  | 0h |  | 0h |  | 30 min |  | 0h |  | 3h30 |  | 1h | [5 empty] | Oral preparation time excluded : |  | Total done percentage for documents part / week : | expected | 0% | 0% | 77.5% | 95% | 97.5% | 100% | 100% | 100%
Human Ressources | Overtime | 2h |  | 2h |  | 2h |  | 8h |  | 8h |  | 20h |  | 42h | [8 empty] | actual | 0% | 1.75% | 41.25% | 83.75% | 97% | 98.75% | 100% | 100%
Human Ressources | Project Time scheduled | 0 | 0h | 1 | 3h15 | 8 | 26h | 6 | 19h30 | 1 | 3h15 | 4 | 13h | 5 | 16h15 | 4 | 13h | 29 | 94h15 | 25 | 81h15 |  |  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8
Category | Name | Half-Days | Hours | Half-Days | Hours | Half-Days | Hours | Half-Days | Hours | Half-Days | Hours | Half-Days | Hours | Half-Days | Hours | Half-Days | Hours | Half-Days | Hours | Half-Days | Hours | Total done percentage for documents part / week : | expected | 0% | 0% | 55% | 77.5% | 85% | 92.5% | 100% | 100%
[8 empty] | Functional : 30th Jan. |  | Technical : 9th Feb. |  | Test Plan : 16 Feb. |  | Final Product : 23 Feb. |  | ORAL Preparation | [6 empty] | actual | 0% | 0% | 25% | 31.25% | 34.5% | 53.75% | 90% | 80%
[24 empty] | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8
[22 empty] | tasks done / to review | expected | 0 | 0 | 19 | 33 | 35 | 44 | 57 | 57
[23 empty] | actual | 0 | 0 | 13 | 25 | 29 | 36 | 51 | 51
[24 empty] | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8
[22 empty] | project time / overtime | project time | 0 | 3.25 | 26 | 19.5 | 3.25 | 13 | 16.25 | 13
[23 empty] | over time | 2 | 2 | 2 | 8 | 8 | 20 | 42 | 0
[24 empty] | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8
[22 empty] | employees satisfaction | expected | 0% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
[23 empty] | actual | 0% | 64% | 64.17% | 71.67% | 71.67% | 78.33% | 80%
In red, the value I have to change here and not anywhere else
No Project Time

## Tasks
[9 empty] | Number of tasks | 57
ALL THE TASKS |  |  |  | The Trello board of assignement and management of the tasks |  |  |  |  | Done/To review tasks | 51
[9 empty] | Doing tasks | 0 | Percentage : | 89.47%
[9 empty] | Remaining tasks | 6
Category | Name of the task | State | Description |  | State menu | Category Menu | is a task ? | done ? | doing ?
Management | Readme.md | Done | create the readme.md of the GitHub repository |  | To Be Done | Management | 1 | 1 | 0
Management | Build the Trello Board | Done | Create all the tags and the columns to manage the tasks on Trello |  | Doing | Functional | 1 | 1 | 0
Management | Project Charter | Done | Redact the project charter and put in on GitHub |  | Reviewing | Technical | 1 | 1 | 0
Management | Client's Meeting | Done | Organize a meeting with the client to clarify some points about the expectations |  | Done | Developement | 1 | 1 | 0
Management | Minutes of the meeting | Done | Summary the meeting with the client |  |  | Q.A. & Tests | 1 | 1 | 0
Management | Weekly report cumul. | Done | Write the weekly reports and make a cumulative on GitHub |  |  |  | 1 | 1 | 0
Management | weekly report 1 | Done | Write the weekly report of week 2 |  |  |  | 1 | 1 | 0
Management | Define all the tasks | Done | make the list of all the tasks, even more than expected to be done |  |  |  | 1 | 1 | 0
Management | Make the KPI dashboard | Done | Have the key informations of the project and the charts to visualize it |  |  |  | 1 | 1 | 0
Management | RACI | Done | Make the RACI (Responsible/accountable/Consulted/Informed) board and put on GitHub |  |  |  | 1 | 1 | 0
Management | Risk & Assomptions | Done | Details the risks and assumptions of the project |  |  |  | 1 | 1 | 0
Management | Gant Chart | Done | Make the Gant chart and put on Github |  |  |  | 1 | 1 | 0
Management | weekly report 2 | Done | Write the weekly report of week 3 |  |  |  | 1 | 1 | 0
Management | weekly report 3 | Done | Write the weekly report of week 4 |  |  |  | 1 | 1 | 0
Management | weekly report 4 | Done | Write the weekly report of week 5 |  |  |  | 1 | 1 | 0
Management | weekly report 5 | Done | Write the weekly report of week 6 |  |  |  | 1 | 1 | 0
Management | weekly report 6 | Done | Write the weekly report of week 7 |  |  |  | 1 | 1 | 0
Management | weekly report 7 | To Be Done | Write the weekly report of week 8 |  |  |  | 1 | 0 | 0
Functional | The mnemonics | Done | chose which instructions we'll use, their name |  |  |  | 1 | 1 | 0
Functional | Opcode's parameters & returns | Done | chose how each instruction works, what it get and return and where |  |  |  | 1 | 1 | 0
Functional | syntax of assembly | Done | conventions of coding in assembly (spaces, comas comments,...) |  |  |  | 1 | 1 | 0
Functional | Architecture's specifications | Done | chose the size and number of registers, the flags and their usage, the memory and how to address it |  |  |  | 1 | 1 | 0
Functional | Encodage in machine code | Done | size of the opcode identifier, rule of encodage in binary, siez of the parameters |  |  |  | 1 | 1 | 0
Functional | compilation and emulation | Done | the steps of the programs which will compile and run assembly through machine code |  |  |  | 1 | 1 | 0
Functional | Personas | Done | Invent the description of people who could be interested in the result of our project |  |  |  | 1 | 1 | 0
Functional | Finish the Functionnal | Done | All the other less important parts of the functional. And validation of the functional. |  |  |  | 1 | 1 | 0
Functional | Documentation for Assembly | Done | Write the normalized documentation for our new assembly language |  |  |  | 1 | 1 | 0
Technical | C Coding conventions | Done | Define the upper/lower case, indentation, rules for naming and so on... |  |  |  | 1 | 1 | 0
Technical | Detail the way to compile | Done | technical part of the first program which reads assembly and writes the binary file |  |  |  | 1 | 1 | 0
Technical | Detail the way to emulate | Done | technical part of the second program which reads interprets the machine code on the virtual processor |  |  |  | 1 | 1 | 0
Technical | Finish the Technical | Done | All the other less important parts of the technical. And validation of the technical. |  |  |  | 1 | 1 | 0
Developement | Read an assembly file | Done | Read a file with a program using our new language and get the right algorithm from it |  |  |  | 1 | 1 | 0
Developement | Instruction into machine code | Done | Encode the algorithm (each instruction) in a binary file executable by the v-processor |  |  |  | 1 | 1 | 0
Developement | Build the virtual components | Done | Allocate memory and handle read/write for the virtual flags, registers and memory. |  |  |  | 1 | 1 | 0
Developement | Clock for instructions | Won't do | Impement a clock to have regular instructions execution based on the number of used clock-cycles |  |  |  | 1 | 0 | 0
Developement | Decode binary file to func. | Done | Read the binary file, and execute the right instruction with the right parameters through the v-processor |  |  |  | 1 | 1 | 0
Developement | Make a stack | Done | have a stack with a stack pointer, push an pop functions working |  |  |  | 1 | 1 | 0
Developement | XOR AND OR NOT operands | Done | obvious |  |  |  | 1 | 1 | 0
Developement | set load copy store | Done | code the 4 functions that assembly often name 'mov' to move data through memory and registers |  |  |  | 1 | 1 | 0
Developement | the 4 basic operations (x/+-) | Done | obvious |  |  |  | 1 | 1 | 0
Developement | noop operand | Done | no operation instruction |  |  |  | 1 | 1 | 0
Developement | Comparison and jump | Done | code a way to compare values and set flags, and jump to another part of the code according to these flags |  |  |  | 1 | 1 | 0
Developement | handle ret and call | Done | the way we execute a kind of 'function' in assembly using stack to save the current code pointer |  |  |  | 1 | 1 | 0
Developement | print on the v-terminal | Won't do | output stream to the virtual terminal , just print some text for now |  |  |  | 1 | 0 | 0
Developement | get keyboard inputs | Won't do | input stream from the virtual terminal, get user input like text or a keypress. |  |  |  | 1 | 0 | 0
Developement | handle semantical errors | Done | detect and provide adequate error message when the compiler encounter a semantical error |  |  |  | 1 | 1 | 0
Developement | handle syntactical errors | Done | detect and provide adequate error message when the compiler encounter a syntatical error |  |  |  | 1 | 1 | 0
Developement | display the v-components | Done | like a debugger, an assembly program can print the content of memory flags or registers easily |  |  |  | 1 | 1 | 0
Developement | write in a data section in ASM | Won't do | be able to store data directly in memory through compilation, without needing an cpu instruction |  |  |  | 1 | 0 | 0
Developement | display pixels (GPU) | Won't do | make a basic graphical interface that can display pixels through a video memory |  |  |  | 1 | 0 | 0
Developement | Write the unit tests for QA | Done | In C programs, write the functions enabling the QA to test if the program works correctly and detect bugs |  |  |  | 1 | 1 | 0
Developement | The Compiler progress | Done | is this first C program finished ? |  |  |  | 1 | 1 | 0
Developement | The Interpreter progress | Done | is this second C program finished ? |  |  |  | 1 | 1 | 0
Q.A. & Tests | Test Plan | Done | Redact the Test Plan to explain how the quality of the project will be checked |  |  |  | 1 | 1 | 0
Q.A. & Tests | Write a bunch of test files | Done | Test the assembly language and its emulation to ensure quality and stability |  |  |  | 1 | 1 | 0
Q.A. & Tests | Unit Testing | Done | Test all the C programs and detect bugs. |  |  |  | 1 | 1 | 0
Q.A. & Tests | Review documents | Done | Ensure that all the documents are qualitative and clear. |  |  |  | 1 | 1 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0
[7 empty] | 0 | 0 | 0

## Gantt chart
█ Forecast █ Actual █ Matching both
|  |  | week 1 | week 2 | week 3 | [7 empty] | week 4 | [5 empty] | week 5 | week 6 |  |  |  | week 7 |  |  |  |  | week 8
| Category | Name of the task |  | Wednesday 17/01 | Monday 22/01 | Monday 22/01 | Tuesday 23/01 | Tuesday 23/01 | Wednesday 24/01 | Thursday 25/01 | Friday 26/01 | Friday 26/02 | Monday 29/01 | Monday 29/01 | Tuesday 30/01 | Thursday 01/02 | Thursday 01/02 | Friday 02/02 | Monday 05/02 | Monday 12/02 | Tuesday 13/02 | Wednesday 14/02 | Friday 16/02 | Monday 19/02 | Monday 19/02 | Tuesday 20/02 | Wednesday 21/02 | Thursday 22/02 | Monday 26/02 | Monday 26/02 | Thursday 29/02 | Thursday 29/02
| Management | Project Charter
| Management | Client's Meeting
| Management | Minutes of the meeting
| Management | Build the Trello Board
| Management | Define all the tasks
| Management | Gant Chart
| Management | Make the KPI dashboard
| Management | Readme.md
| Management | Risk & Assomptions
| Management | RACI
| Management | Weekly report cumul.
| Management | weekly report 1
| Management | weekly report 2
| Management | weekly report 3
| Management | weekly report 4
| Management | weekly report 5
| Management | weekly report 6
| Management | weekly report 7
| Functional | The mnemonics
| Functional | Opcode's parameters & returns
| Functional | syntax of assembly
| Functional | Architecture's specifications
| Functional | Encodage in machine code
| Functional | compilation and emulation
| Functional | Personas
| Functional | Finish the Functionnal
| Functional | Documentation for Assembly
| Technical | C Coding conventions
| Technical | Detail the way to compile
| Technical | Detail the way to emulate
| Technical | Finish the Technical
| Developement | Read an assembly file
| Developement | Instruction into machine code
| Developement | Build the virtual components
| Developement | Decode binary file to func.
| Developement | Make a stack
| Developement | XOR AND OR NOT operands
| Developement | set load copy store
| Developement | the 4 basic operations (x/+-)
| Developement | noop operand
| Developement | Comparison and jump
| Developement | handle ret and call
| Developement | print on the v-terminal
| Developement | get keyboard inputs
| Developement | handle semantical errors
| Developement | handle syntactical errors
| Developement | display the v-components
| Developement | write in a data section in ASM
| Developement | display pixels (GPU)
| Developement | Write the unit tests for QA
| Developement | The Compiler progress
| Developement | The Interpreter progress
| Q.A. & Tests | Test Plan
| Q.A. & Tests | Write a bunch of test files
| Q.A. & Tests | Unit Testing
| Q.A. & Tests | Review documents
No Project Time No Project Time No Project Time